## Cover
PROJECT REPORT
GROUP 5
This is a work status report for the week, and identifies plans and goals for the following weeks.
The report is summarized at the end of each week and will be updated in the future.
Members:
+ ĐINH TIẾN LÂM (HE153097);
+ NGÔ QUANG HUY (HE153653);
+ NGUYÊN NAM PHƯƠNG (HE153074);
+ NGUYỄN TRUNG KIÊN (HE153296);
+ NGUYỄN ĐÌNH TRUNG ĐỨC (HE153148);

## Week5
PROJECT REPORT
Group | LIBRARY SYSTEM
Week | 04/10/2021-10/10/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Writing specification documents | In Progress | none
2 | Learn about ASP.NET MVC | In Progress | none
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Overall Description + Functional Requirements Specification (Librarian) + Other Nonfunctional Requirements | Đinh Tiến Lâm | Design and Implementation Constraints + User Documentation + Assumptions and Dependencies + Login/Logout + Add Publication + Add Book + Security requirement + Sorfware quality attributes
2 | Introduction + Functional Requirements Specification (Librarian) + Other Nonfunctional Requirements | Nguyễn Đình Trung Đức | Purpose + System Purpose + Definitions, Acronyms and Abbreviations + View book report + Add branch + Add student + View student report + Performance requirement + Design constraints + Safety requirement
3 | Introduction + Functional Requirements Specification (Student) + External Interface Requirements | Ngô Quang Huy | Document Conventions + Intended Audience and Reading Suggestions + Project Scope + Change password + My report + Penalty report + View book + User Interfaces
4 | Introduction + Overall Description + Functional Requirements Specification (Librarian) + Database | Nguyễn Trung Kiên | References + Product/System Perspective + System/Product Features + Issue book + Issue report + Return book + Penalty + Appendix A: Database diagram + Appendix B: Database entity
5 | Overall Description + Functional Requirements Specification (Student) + External Interface Requirements | Nguyễn Nam Phương | User requirements + User Classes and Characteristics + Operating Environment + Login/Logout + View report + Edit Account + Hardware Interfaces + Sorfware Interfaces + Communication Interfaces
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | none
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | none
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | none
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C18: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week6
PROJECT REPORT
Group | LIBRARY SYSTEM
Week | 11/10/2021-17/10/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week7
PROJECT REPORT
Group | LIBRARY SYSTEM
Week | 18/10/2021-24/10/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week8
PROJECT REPORT
Group | LIBRARY SYSTEM
Week | 25/10/2021-31/10/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week9
PROJECT REPORT
Group | LIBRARY SYSTEM
Week | 01/11/2021-07/11/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
Pending
In Progress
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
KienNT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
Pending
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C17: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue